## Gantt Chart Template
| PROJECT TITLE | Mobile Apps to Reduce Cross-Race Recognition Deficit |  |  |  |  | COMPANY NAME | [8 empty] | University of Colorado Boulder, Department of Psychology and Neuroscience
| PROJECT MANAGER | Alan Paradise |  |  |  |  | DATE | [8 empty] | 2020-10-15
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [19 empty] | PHASE FIVE | [14 empty] | PHASE SIX | [14 empty] | PHASE SEVEN | [14 empty] | PHASE EIGHT | [14 empty] | PHASE NINE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (Days) | PCT OF TASK COMPLETE | WEEK OF 9/13 |  |  |  |  | WEEK OF 9/20 |  |  |  |  | WEEK OF 9/27 |  |  |  |  | WEEK OF 10/4 |  |  |  |  | WEEK OF 10/11 |  |  |  |  | WEEK OF 10/18 |  |  |  |  | WEEK OF 10/25 |  |  |  |  | WEEK OF 11/1 |  |  |  |  | WEEK OF 11/8 |  |  |  |  | WEEK OF 11/15 |  |  |  |  | WEEK OF 11/22 |  |  |  |  | WEEK OF 11/29 |  |  |  |  | WEEK OF 12/6 |  |  |  |  | WEEK OF 1/12 |  |  |  |  | WEEK OF 1/19 |  |  |  |  | WEEK OF 1/26 |  |  |  |  | WEEK OF 2/2 |  |  |  |  | WEEK OF 2/9 |  |  |  |  | WEEK OF 2/16 |  |  |  |  | WEEK OF 2/23 |  |  |  |  | WEEK OF 3/1 |  |  |  |  | WEEK OF 3/8 |  |  |  |  | WEEK OF 3/15 |  |  |  |  | WEEK OF 3/22 |  |  |  |  | WEEK OF 3/29 |  |  |  |  | WEEK OF 4/5 |  |  |  |  | WEEK OF 4/12 |  |  |  |  | WEEK OF 4/19 |  |  |  |  | WEEK OF 4/26
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Introduction
1.1 | Member introductions | All | 2020-09-13 | 2020-09-20 | 7 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
1.2 | Organize team meetings | Front End | 2020-09-13 | 2020-09-20 | 7 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
1.3 | Set administrative roles | All | 2020-09-13 | 2020-09-20 | 7 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
1.4 | Create a team logo | Front End | 2020-09-13 | 2020-09-20 | 7 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2 | Administrative
2.1 | Contact last years team | Front End | 2020-09-20 | 2020-09-27 | 7 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2.2 | Download required IDE`s | All | 2020-09-20 | 2020-09-27 | 7 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2.3 | Request previous documentation | All | 2020-09-20 | 2020-09-27 | 7 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2.4 | Request code/database access | Front End | 2020-09-20 | 2020-09-27 | 7 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2.5 | Set up a new GitHub account | Front End | 2020-09-13 | 2020-09-27 | 14 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2.5.1 | Create folders to organize the repository | Front End | 2020-09-13 | 2020-09-27 | 14 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2.5.2 | Grant access to all interested parties | Front End | 2020-09-13 | 2020-09-27 | 14 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2.5.3 | Create a new readme | All | 2020-09-13 | 2020-09-27 | 14 | 100% | bar: WEEK OF 9/13 M to WEEK OF 9/20 F
2.5.4 | Keep the repository up to date | All | 2020-09-13 | 2021-05-06 | 233 | 100%
2.6 | Create and submit a status report every week | All | 2020-10-04 | 2021-05-06 | 212 | 100%
2.7 | Submit peer evaluations | All | 2020-12-01 | 2020-12-07 | 6 | 100%
3 | Meetings
3.1 | Contact sponsor to introduce ourselves | All | 2020-09-16 | 2020-09-28 | 12 | 100% | bar: WEEK OF 9/13 R to WEEK OF 9/27 M
3.2 | Contact TA to introduce ourselves | All | 2020-09-22 | 2020-10-06 | 14 | 100% | bar: WEEK OF 9/20 M to WEEK OF 9/27 W
3.3 | Organize Team meetings every week | All | 2020-09-13 | 2021-05-06 | 233 | 100%
3.3.1 | Take and record attendance | Front End | 2020-09-13 | 2021-05-06 | 233 | 100%
3.4 | Organize Sponsor meetings every two weeks | Front End | 2020-09-13 | 2021-05-06 | 233 | 100%
3.4.1 | Take and record attendance | Front End | 2020-09-13 | 2021-05-06 | 233 | 100%
3.5 | Organize TA meetings every two weeks | Front End | 2020-09-13 | 2021-05-06 | 233 | 100%
3.5.1 | Take and record attendance | Front End | 2020-09-13 | 2021-05-06 | 233 | 100%
4 | Familiarize with the existing code base
4.1 | Download previous codebase | All | 2020-09-13 | 2020-11-01 | 48 | 100% | bar: WEEK OF 9/13 M to WEEK OF 11/1 F
4.2 | Update our work environments to accept the previous codebase | All | 2020-09-13 | 2020-11-01 | 48 | 100% | bar: WEEK OF 9/13 M to WEEK OF 11/1 F
4.3 | Examine and understand the previous teams work | All | 2020-09-22 | 2020-11-01 | 39 | 100% | bar: WEEK OF 9/20 M to WEEK OF 11/1 F
4.3.1 | Request previous documentation | All | 2020-09-22 | 2020-11-01 | 39 | 100% | bar: WEEK OF 9/20 M to WEEK OF 11/1 F
4.3.2 | Request code/database access | Front End | 2020-09-22 | 2020-11-01 | 39 | 100% | bar: WEEK OF 9/20 M to WEEK OF 11/1 F
4.4 | Test the previous teams work | All | 2020-09-22 | 2020-11-01 | 39 | 100% | bar: WEEK OF 9/20 M to WEEK OF 11/1 F
4.5 | Get the project working | All | 2020-09-27 | 2020-11-01 | 34 | 100% | bar: WEEK OF 9/20 M to WEEK OF 11/1 F
4.5.1 | Create accounts on the platform | All | 2020-10-04 | 2020-11-01 | 27 | 100% | bar: WEEK OF 10/4 M to WEEK OF 11/1 F
4.5.2 | Get the iOS app working | Front End | 2020-10-04 | 2020-11-01 | 27 | 100% | bar: WEEK OF 10/4 M to WEEK OF 11/1 F
4.5.3 | Get the Android app working | Front End | 2020-10-04 | 2020-11-01 | 27 | 100% | bar: WEEK OF 10/4 M to WEEK OF 11/1 F
5 | Scope
5.1 | Create Preliminary Scope Statement | All | 2020-10-04 | 2020-11-20 | 46 | 100% | bar: WEEK OF 10/4 M to WEEK OF 11/15 F
5.2 | Develop Project Charter | All | 2020-10-04 | 2020-11-20 | 46 | 100% | bar: WEEK OF 10/4 M to WEEK OF 11/15 F
5.3 | Deliverable: Submit Project Charter | All | 2020-10-06 | 2020-11-20 | 44 | 100% | bar: WEEK OF 10/4 T to WEEK OF 11/15 F
5.4 | Project Sponsor Review Project Charter | All | 2020-10-06 | 2020-11-20 | 44 | 100% | bar: WEEK OF 10/4 T to WEEK OF 11/15 F
5.4.1 | Modify Project Charter if needed | All | 2020-10-06 | 2020-11-20 | 44 | 100% | bar: WEEK OF 10/4 T to WEEK OF 11/15 F
5.4.2 | Resubmit project charter for review if needed | All | 2020-10-20 | 2020-11-20 | 30 | 100% | bar: WEEK OF 10/18 T to WEEK OF 11/15 F
5.5 | Project Charter Signed/Approved | All | 2020-10-20 | 2020-11-20 | 30 | 100% | bar: WEEK OF 10/18 T to WEEK OF 11/15 F
6 | Project Planning
6.1 | Determine Project Roles | All | 2020-09-13 | 2020-12-07 | 84 | 100%
6.2 | Create a Project Plan | All | 2020-09-13 | 2020-12-07 | 84 | 100%
6.2.1 | Determine Project development (Agile/Scrum) | All | 2020-11-20 | 2020-12-07 | 17 | 100% | bar: WEEK OF 11/15 F to WEEK OF 12/6 F
6.2.2 | Develop Project Plan | All | 2020-10-20 | 2020-12-07 | 47 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.2.3 | Submit a Project Plan | All | 2020-10-20 | 2020-12-07 | 47 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.2.4 | Milestone: Project Plan Approved | All | 2020-10-20 | 2020-12-07 | 47 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.3 | Create Work Breakdown Structure | All | 2020-10-25 | 2020-12-07 | 42 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.3.1 | Develop a work breakdown structure | All | 2020-10-25 | 2020-12-07 | 42 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.3.2 | Review work breakdown structure | All | 2020-10-25 | 2020-12-07 | 42 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.3.3 | Submit work breakdown structure | All | 2020-10-25 | 2020-12-07 | 42 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.4 | Create Requirements Document | All | 2020-10-25 | 2020-12-07 | 42 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.4.1 | Develop Requirements Document | All | 2020-10-25 | 2020-12-07 | 42 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.4.2 | Review Requirements Document | All | 2020-10-25 | 2020-12-07 | 42 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
6.4.3 | Submit Requirements Document | All | 2020-10-25 | 2020-12-07 | 42 | 100% | bar: WEEK OF 10/25 M to WEEK OF 11/15 F
7 | Extending Racial Group & Gender Sets
7.1 | Acquire new face sets/groups | Back End | 2021-01-20 | 2021-02-01 | 11 | 15% | bar: WEEK OF 1/19 M to WEEK OF 1/26 F
7.2 | Data processing/database design | Back End | 2020-10-25 | 2021-02-01 | 96 | 15% | bar: WEEK OF 10/4 M to WEEK OF 1/26 F
7.3 | Risk management | Back End | 2020-10-25 | 2021-03-31 | 156 | 30% | bar: WEEK OF 10/25 M to WEEK OF 3/15 F
8 | Forced Choice training
8.1 | Enable/ debug force choice training | Back End | 2021-01-20 | 2021-03-31 | 71 | 45% | bar: WEEK OF 1/19 M to WEEK OF 3/15 F
8.2 | Update last years work | All | 2021-01-20 | 2021-03-31 | 71 | 30% | bar: WEEK OF 1/19 M to WEEK OF 3/15 F
9 | Add new face sets to the system
9.1 | Design difficulty algorithm | Back End | 2021-01-20 | 2021-03-31 | 71 | 5% | bar: WEEK OF 1/19 M to WEEK OF 3/15 F
9.2 | Create and add datasets | Back End | 2021-01-20 | 2021-03-31 | 71 | 10% | bar: WEEK OF 1/19 M to WEEK OF 3/15 F
9.3 | Design and implement performance evaluation algorithm | Back End | 2021-01-20 | 2021-03-31 | 71 | 10% | bar: WEEK OF 1/19 M to WEEK OF 3/15 F
9.4 | Design and implement a scoring system | Back End | 2021-01-20 | 2021-03-31 | 71 | 5% | bar: WEEK OF 1/19 M to WEEK OF 3/15 F
9.5 | Design and implement a system to allow the participant to chose face set | Back End | 2021-01-20 | 2021-03-31 | 71 | 15% | bar: WEEK OF 1/19 M to WEEK OF 3/15 F
10 | Back end
10.1 | Understand previous semesters database | Back End | 2020-11-01 | 2020-12-04 | 33 | 90% | bar: WEEK OF 11/1 M to WEEK OF 11/29 R
10.2 | Update database | Back End | 2021-01-20 | 2021-04-25 | 95 | 10% | bar: WEEK OF 1/19 M to WEEK OF 4/26 F
10.3 | Make sure the database is robust | Back End | 2021-02-01 | 2021-04-25 | 84 | 50% | bar: WEEK OF 2/2 M to WEEK OF 4/26 F
10.4 | Make or manage API`s | Back End | 2021-02-01 | 2021-04-25 | 84 | 0% | bar: WEEK OF 2/2 M to WEEK OF 4/26 F
10.5 | Make sure the front end team is getting the information they need | Back End | 2021-01-15 | 2021-02-01 | 16 | 0% | bar: WEEK OF 2/2 M to WEEK OF 4/26 F
11 | Front end
11.1 | Redesign a new UI | Frond End | 2020-10-01 | 2020-12-01 | 60 | 100% | bar: WEEK OF 9/27 R to WEEK OF 11/29 F
11.2 | Submit the new UI for approval | Frond End | 2020-10-20 | 2020-11-01 | 11 | 100% | bar: WEEK OF 10/18 T to WEEK OF 11/1 F
11.3 | Implement the new design | Frond End | 2021-02-01 | 2021-04-25 | 84 | 0% | bar: WEEK OF 2/2 M to WEEK OF 4/26 F
11.4 | Update the website with the new UI | Frond End | 2021-02-01 | 2021-04-25 | 84 | 0% | bar: WEEK OF 2/2 M to WEEK OF 4/26 F
11.5 | Update the mobile version with the new UI | Frond End | 2021-02-01 | 2021-04-25 | 84 | 0% | bar: WEEK OF 2/2 M to WEEK OF 4/26 F
11.6 | Fix previous teams responsiveness issues | Frond End | 2021-02-01 | 2021-04-25 | 84 | 0% | bar: WEEK OF 2/2 M to WEEK OF 4/26 F
12 | Testing
12.1 | test iOS app | All | 2021-03-01 | 2021-04-25 | 54 | 15% | bar: WEEK OF 3/1 M to WEEK OF 4/26 F
12.2 | test android app | All | 2021-03-01 | 2021-04-25 | 54 | 15% | bar: WEEK OF 3/1 M to WEEK OF 4/26 F
12.3 | Test the new web app | All | 2021-03-01 | 2021-04-25 | 54 | 15% | bar: WEEK OF 3/1 M to WEEK OF 4/26 F
12.4 | Stress test the frontend | All | 2021-03-01 | 2021-04-25 | 54 | 0% | bar: WEEK OF 3/1 M to WEEK OF 4/26 F
12.5 | Stress test the backend | All | 2021-03-01 | 2021-04-25 | 54 | 0% | bar: WEEK OF 3/1 M to WEEK OF 4/26 F
12.6 | Test the database | All | 2021-03-01 | 2021-04-25 | 54 | 0% | bar: WEEK OF 3/1 M to WEEK OF 4/26 F
13 | Publisihing
13.1 | Publish a new iOS app | Frond End | 2021-04-25 | 2021-05-01 | 6 | 0% | bar: WEEK OF 4/26 M to WEEK OF 4/26 F
13.2 | Publish a new android app | Frond End | 2021-04-25 | 2021-05-01 | 6 | 0% | bar: WEEK OF 4/26 M to WEEK OF 4/26 F
13.3 | Publish a new web app | Frond End | 2021-04-25 | 2021-05-01 | 6 | 0% | bar: WEEK OF 4/26 M to WEEK OF 4/26 F
13.4 | Create documentation for the iOS app | Frond End | 2021-04-25 | 2021-05-01 | 6 | 15% | bar: WEEK OF 4/26 M to WEEK OF 4/26 F
13.5 | Create documentation for the android app | Frond End | 2021-04-25 | 2021-05-01 | 6 | 15% | bar: WEEK OF 4/26 M to WEEK OF 4/26 F
13.6 | Create documentation for the web app | Frond End | 2021-04-25 | 2021-05-01 | 6 | 15% | bar: WEEK OF 4/26 M to WEEK OF 4/26 F
13.7 | Update Github repository readme | Frond End | 2021-04-25 | 2021-05-01 | 6 | 100% | bar: WEEK OF 4/26 M to WEEK OF 4/26 F
14 | Presenting
14.1 | Semester 1 Presentation | All | 2020-11-01 | 2020-11-22 | 21 | 100% | bar: WEEK OF 11/1 M to WEEK OF 11/15 F
14.1.1 | Create the first-semester presentation | All | 2020-11-01 | 2020-11-22 | 21 | 100% | bar: WEEK OF 11/1 M to WEEK OF 11/15 F
14.1.2 | Rehearse presentation | All | 2020-11-01 | 2020-11-22 | 21 | 100% | bar: WEEK OF 11/1 M to WEEK OF 11/15 F
14.1.3 | Record the presentation | All | 2020-11-01 | 2020-11-22 | 21 | 100% | bar: WEEK OF 11/1 M to WEEK OF 11/15 F
14.1.4 | Submit the presentation | All | 2020-11-01 | 2020-11-22 | 21 | 100% | bar: WEEK OF 11/1 M to WEEK OF 11/15 F
14.2 | Semester 2 Presentation | All | 2021-04-01 | 2021-04-30 | 29 | 0% | bar: WEEK OF 3/29 R to WEEK OF 4/26 F
14.2.1 | Create the second-semester presentation | All | 2021-04-01 | 2021-04-30 | 29 | 0% | bar: WEEK OF 3/29 R to WEEK OF 4/26 F
14.2.2 | Rehearse presentation | All | 2021-04-01 | 2021-04-30 | 29 | 0% | bar: WEEK OF 3/29 R to WEEK OF 4/26 F
14.2.3 | Record the presentation | All | 2021-04-01 | 2021-04-30 | 29 | 0% | bar: WEEK OF 3/29 R to WEEK OF 4/26 F
14.2.4 | Submit the presentation | All | 2021-04-01 | 2021-04-30 | 29 | 0% | bar: WEEK OF 3/29 R to WEEK OF 4/26 F